## SHB Form
Health, Safety & Environmental Department
HSE site inspection performance evaluations
Project : Social Housing Building | Inspection No: 1
Location: Badr City | Date of Inspection: 06/07/2025
Inspector: Tamer Agamy
SPMS Ratings for: ( Social Housing Building )
Positive Findings:
1- Flammable materials are secured and stored
2-Hand tools are in good condition and quality.
3- drinking water provided at work place with enough quantity
4- Toilets are clean and detergents are provided
Negative findings and Areas for Improvement:
1- Poor arrangement of materials
2- No safety management on site.. 3- No safety & environment control measures on site. 4- No PPE or fall protection on site.
Date of Next Inspection:
Name of Inspector: Tamer Agamy |  | Date: 06/07/2025
SPMS Element | Score
Health and Safety Management
1.0 HSE Organisation | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
1.1 HSE Policy Issued and Displayed |  | A |  |  |  |  | 0
1.2 Management HSE Responsibilities and Duties in place |  | A |  |  |  |  | 0
1.3 Responsibilities and Duties understood & followed |  | A |  |  |  |  | 0
1.4 HSE Appointments made for Fire, First Aid, etc. |  | A |  |  |  |  | 0
1.5 Adequate HSE Staff appointed for the contract |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 20
Percentage |  |  |  | 0 | %
2.0 Project Health and Safety Plan | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
2.1 HSE Plan in Place and Implemented |  | A |  |  |  |  | 0
2.2 Plan up to Date with project requirements and risk |  | A |  |  |  |  | 0
2.3 Management Reviews completed and Plan Updated |  | A |  |  |  |  | 0
2.4 Issued to Senior Management |  | A |  |  |  |  | 0
2.5 Issued to Contractors |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 20
Rating |  |  |  | 0 | %
3.0 General HSE Communication | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
3.1 Toolbox talks completed as per schedule / Requirements |  | A |  |  |  |  | 4
3.2 Specific Toolbox talks to Project / Requirements |  | A |  |  |  |  | 0
3.3 Toolbox talks relevant to weekly taskes |  | A |  |  |  |  | 0
3.4 Daily brief to HSE issues on site |  | A |  |  |  |  | 0
3.5 HSE Notice Boards Posted / Up to Date |  | A |  |  |  |  | 0
3.6 Key information communicated to Engineer / Supervisores |  | A |  |  |  |  | 0
3.7 Project management committed to guarantee that the contractors provide an appropriate PPEs for the assigned job. |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 28
Rating |  |  |  | 0 | %
SPMS Element | Score
Inspection
4.0 Health and Safety Inductions | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
4.1 HSE Induction Specific to Project/ PM/ CM |  | A |  |  |  |  | 0
4.2 Project management committed to refer the employees / contractor to the OH&S Department before starting work to obtain HSE induction and ensure its compliance with safety standards on first Day of Work. |  | A |  |  |  |  | 0
4.3 Subcontractors employees included & sign |  | A |  |  |  |  | 0
4.4 Induction Records and Registers Maintained. |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 16
Rating |  |  |  | 0 | %
5.0 Project HSE Training | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
5.1 HSE Training Needs Identified |  | A |  |  |  |  | 0
5.2 In line with project requirements and risk areas |  | A |  |  |  |  | 0
5.3 Reviews / follow-up of training completed |  | A |  |  |  |  | 0
5.4 Task /Trade Training Conducted work permit related |  | A |  |  |  |  | 0
5.5 Records /Registers Maintained |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 20
Rating |  |  |  | 0 | %
6.0 Fire Safety Management | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
6.1 Fire risk assessments completed for all areas |  | A |  |  |  |  | 0
6.2 Personnel trained in fire safety arrangements |  | A |  |  |  |  | 0
6.3 Fire Control zones identified and protected |  | A |  |  |  |  | 0
6.4 Fire Incidents investigated and actions closed out |  | A |  |  |  |  | 0
6.5 Permit to work system for high risk activities / fire exposure |  | A |  |  |  |  | 0
6.6 Fire Management Procedure in Place |  | A |  |  |  |  | 0
6.7 Fire Fighting Equipment Checked / Log of Inspections |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 24
Rating |  |  |  | 0 | %
HSE Management total score |  |  |  | 144
HSE Management total score including the N/A |  |  |  | 128
HSE Management achieved score |  |  |  | 0
HSE Management percentage % |  |  |  | 0 | %
SPMS Element | Score
Risk Management
7.0 Project Hazard & Risk Assessment | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
7.1 General Hazard and Risk Assessment completed ( project) |  | A |  |  |  |  | 0
7.2 Reviewed and Updated inline with project activities |  | A |  |  |  |  | 0
7.3 workforce attaned the risk Decision |  | A |  |  |  |  | 0
7.4 Control Measures identified and implemented |  | A |  |  |  |  | 0
7.5 Personnel Trained/Competent to conduct risk assessments |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 20
Rating |  |  |  | 0 | %
8.0 Accident / Incident Management | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
8.1 Procedure developed for the project and implemented |  | A |  |  |  |  | 0
8.2 Investigation completed with right root cause |  | A |  |  |  |  | 0
8.3 Investigation Reports issued to senior management |  | A |  |  |  |  | 0
8.4 Root cause reviewed with the procedures |  | A |  |  |  |  | 0
8.5 Projects Management Involved in Investigation Process |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 20
Rating |  |  |  | 0 | %
9.0 Subcontractors Risk Management / Communication | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
9.1 Generic Hazard and Risk Identified for Work Activities |  | A |  |  |  |  | 0
9.2 Incorporated into overall risk profile for the project |  | A |  |  |  |  | 0
9.3 HSE Alerts Issued |  | A |  |  |  |  | 0
9.4 Contractors inducted and informed of key processes |  | A |  |  |  |  | 0
9.5 Method Statements produced by subcontractors |  | A |  |  |  |  | 0
9.6 A pre-start meeting must be held with all sub-contractors |  | A |  |  |  |  | 0
9.7 Committed to apply A full scope evaluation for the sub-contractors to ensure that they are complying to HSE rules (Induction, PPE, underage policy, pre-start meeting, etc. |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 28
Rating |  |  |  | 0 | %
10.0 Chemical management | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
10.1 Storage conditions are acceptable in storage areas |  | A |  |  |  |  | 0
10.2 All chemicals are clearly identified |  | A |  |  |  |  | 0
10.3 Chemical products used on site are in second containment |  | A |  |  |  |  | 0
10.4 Spill kits are available on site at the areas where there potentially a spill could happen |  | A |  |  |  |  | 0
10.5 MSDS are available for the chemical use |  | A |  |  |  |  | 0
10.6 Warehouse committed not to receiving any supply of chemicals without supplying MSDS to the HSE Department In the project. |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 20
Rating |  |  |  | 0 | %
Risk Management total score |  |  |  | 80
Risk Management total score including the N/A |  |  |  | 88
Risk Management achieved score |  |  |  | 0
Risk Management percentage % |  |  |  | 0 | %
n
n
SPMS Element | Score
Inspections
11.0 HSE inspection | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
11.1 HSE Inspection planned and conducted to programme |  | A |  |  |  |  | 0
11.2 An inspection must be done by a competent person |  | A |  |  |  |  | 0
11.3 Results of Inspection communicated and action identified |  | A |  |  |  |  | 0
11.4 Inspection covering health and safety plan + key risk of project |  | A |  |  |  |  | 0
11.5 Inspection Analysis in line with works and risk rated |  | A |  |  |  |  | 0
11.6 Results discussed in senior management meetings |  | A |  |  |  |  | 0
11.7 The Supervisors & Sub-contractors Committed to use an inspected equipments. |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 24
Rating |  |  |  | 0 | %
12.0 Cold Work Perimt | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
12.1 Are the work permit in Place |  | A |  |  |  |  | 0
12.2 Work Permit including all work related |  | A |  |  |  |  | 0
12.3 Work Permit signed from each responsibles |  | A |  |  |  |  | 0
12.4 Work permit closed on time |  | A |  |  |  |  | 0
12.5 The risks and preventive measures related to the work permit are identified by the responsible supervisor and followed up and implemented |  | A |  |  |  |  | 0
12.6 Work Permit log avalibale on HSE Office |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 24
Rating |  |  |  | 0 | %
Inspections total score |  |  |  | 40
Inspections total score including the N/A |  |  |  | 48
Inspections achieved score |  |  |  | 0
Inspections percentage % |  |  |  | 0 | %
SPMS Element | Score
General Site Performance
13.0 General Site Performance | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
13.1 Workers using correct PPE |  | A |  |  |  |  | 0
13.2 Tools and equipment being used by operative safe to use |  |  |  | A |  |  | 2
13.3 Safety Sign visible and located in prominent areas |  | A |  |  |  |  | 0
13.4 Permit in place for work activity and in compliance |  | A |  |  |  |  | 0
13.5 Emergency access is clear to be in use |  | A |  |  |  |  | 0
13.6 Electrical leads/equipment in safe condition & protected |  | A |  |  |  |  | 0
13.7 Housekeeping maintained to acceptable levels of safety |  | A |  |  |  |  | 0
13.8 Fire Protection measures in place .i.e. fire points |  |  |  | A |  |  | 2
13.9 Committed to apply up An appropriate lighting system during night shift |  | A |  |  |  |  | 0
13.10 Walkways and common areas free from obstructions |  |  |  | A |  |  | 2
|  | Total Score |  |  |  |  | 6 | 40
Rating |  |  |  | 15 | %
14.0 Maintenance & Fabrication Workshop | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
14.1 Lighting is sufficient |  |  |  |  | A |  | 3
14.2 Grinding machine has a protection cover and adequate desk. |  | A |  |  |  |  | 0
14.3 Electrical equipment and tools are inspected with color codes. |  | A |  |  |  |  | 0
14.4 Flammable materials are secured and stored |  |  |  |  | A |  | 3
14.5 Firefighting system planed and implemented |  | A |  |  |  |  | 0
14.6 Hand tools are in good condition and quality. |  |  |  |  | A |  | 3
14.7 Handling used oil procedures are followed in a safe practice an |  |  |  |  | A |  | 3
14.8 All precautions for hot work (welding, cutting) are implemented. |  |  |  | A |  |  | 2
14.9 Housekeeping and material arrangement . |  |  | A |  |  |  | 1
14.10 Are all employees have a suitable PPE and appropriate to their activates? |  |  | A |  |  |  | 1
Smoking prohibition signs are posted in the place and clear for all workers and visitors. |  | A |  |  |  |  | 0
14.12 Mobile tank must have an earthing |  | A |  |  |  |  | 0
14. 13 Safety signs are available in all workplace. |  |  | A |  |  |  | 1
14.14 Floors are flatting and clean against slipping hazards. |  | A |  |  |  |  | 0
14.15 Committed to provide Skill level certificate for (grinding machine operator). |  | A |  |  |  |  | 0
14.16 Waste management procedures are followed. |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 17 | 60
Rating |  |  |  | 28.3333 | %
15.0 Lifting and rigging operations | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
15.1 Does all lifting and rigging equipment are inspected and color coded. |  | A |  |  |  |  | 0
15.2 Calibration certificates for all lifting equipment and gears are valid and provided inside the crane. |  | A |  |  |  |  | 0
15.3 Are the operators, riggers and banks man trained and competent? |  |  |  | A |  |  | 2
15.4 Pre use inspection is carried out? |  | A |  |  |  |  | 0
15.5 Is the critical lifting operation assessed and planned by competent person? |  | A |  |  |  |  | 0
15.6 A drug test must be held for crane operators & riggers |  | A |  |  |  |  | 0
15.7 A communiction method between operators & riggers must be provided, tested and sufficient. |  | A |  |  |  |  | 0
15.8 Skill level certificate must be provided for (operators, riggers) |  | A |  |  |  |  | 0
15.9 Operators licenses are available and valid |  |  |  | A |  |  | 2
|  | Total Score |  |  |  |  | 4 | 36
Rating |  |  |  | 11.1111 | %
16.0 Hot works (cutting & Welding) | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
16.1 Hot work permit copy is provided at work place. |  | A |  |  |  |  | 0
16.2 Are the work permit signed from each one |  | A |  |  |  |  | 0
16.3 Are the work Permit is closed on time |  | A |  |  |  |  | 0
16.4 Fire extinguishers and blankets are available on site for the hot works. |  | A |  |  |  |  | 0
16.5 Are all welding machines inspected and in a good condition and color coded. |  | A |  |  |  |  | 0
16.6 Grinding machine has a protection cover and adequate desk. |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 24
Rating |  |  |  | 0 | %
17.0 Working at height and fall protection | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
17.1 Personal fall arrest system are correctly used (well worn, use of suitable anchor point…) |  | A |  |  |  |  | 0
17.2 All scaffolds are in good conditions and inspected and tagged. By the right scaffolding inspectors |  | A |  |  |  |  | 0
17.3 Safety Harnesses and lanyard in a good condition and used correctly. |  | A |  |  |  |  | 0
17.4 Are the scaffolders trained and competent?( Training Sheet avalibale) |  | A |  |  |  |  | 0
17.5 Does all workers assigned to work at heights received training? ( Training Sheet avalibale) |  | A |  |  |  |  | 0
17.6 Does the scaffold design prevent falling of people and objects (toe board, handrails, midrails and access ladder) |  | A |  |  |  |  | 0
17.7 Are the scaffold material in a good condition and quality? |  | A |  |  |  |  | 0
17.8 If the scaffold highest more than 7 meters is attached in fixed wall or anchor point 4 meters. |  | A |  |  |  |  | 0
17.9 Committed to provide Skill level certificate for (scaffold technicians) |  | A |  |  |  |  | 0
17.10 Stop any ongoing work during the erictionof scaffold or if there are works at heights in this area |  | A |  |  |  |  | 0
17.11 A design or a calculation sheet must be provided for scaffold |  | A |  |  |  |  | 0
17.12 are the scaffolding logs are avalibale |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 44
Rating |  |  |  | 0 | %
18.0 Camp accommodation | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
18.1 Level of housekeeping and cleanliness of the rooms is acceptable? | N/A
18.2 Emergency evacuation procedures are in place and followed | N/A
18.3 Assembly point identified and known to everyone? | N/A
18.4 Toilets are clean and soap is provided? | N/A
18.5 Number of toilets are enough for worker? | N/A
18.6 Sewage tank is designed underground and covered well? | N/A
18.7 Sewage disposal is carrying out by approved company? | N/A
18.8 Gas cylinders are used in cooking are secured and placed in a safe zone and equipped with regulator. | N/A
18.9 Firefighting system planed and implemented, adequate number of fire extinguishers are in place and inspected. | N/A
|  | Total Score |  |  |  |  | 0 | 0
Rating |  |  |  | N/A | %
19.0 Electrical Hazards | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
19.1 All electrical installations/materials including temporary wiring, panels, boxes and fittings are grounded? |  | A |  |  |  |  | 0
19.2 All electrical panels and fittings are closed, locked, are provided with external emergency breakers and correctly identified with electrical risk tags |  | A |  |  |  |  | 0
19.3 All electrical panels & generators must be top guarded to be protected from rain & sun |  | A |  |  |  |  | 0
19.4 All electrical panels must contain a GFCI & a mirror |  | A |  |  |  |  | 0
19.5 An extinguisher is present near each electrical panel, generator |  | A |  |  |  |  | 0
19.6 All electrical materials (cables, tools…) are in good condition, quarterly inspected and marked? |  | A |  |  |  |  | 0
19.7 Safe cables management is applied at the work place? |  | A |  |  |  |  | 0
19.8 Lockout & tag out (LOTO) system is implemented and followed by all people? |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 32
Rating |  |  |  | 0 | %
20.0 Excavations. | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
20.1 Are all underground hazard and utilities (pipe lines, elec. cables, communication….etc.) been identified? |  |  |  | A |  |  | 2
20.2 Excavation methods (shoring, pinching and sloping) are used to prevent collapse of excavation? |  |  |  | A |  |  | 2
20.3 Warning signs and hard barriers around excavation are in good state to prevent falling people and equipment? |  | A |  |  |  |  | 0
20.4 Daily excavation inspection sheet is correctly fulfilled for each excavation? |  | A |  |  |  |  | 0
20.5 Suitable and safe means of access/egress (1 access ramp or ladder every 10 meters) |  |  |  |  | A |  | 3
20.6 Excavation permit copy in place? |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 7 | 24
Rating |  |  |  | 29.1667 | %
21.0 Emergency Preparedness. | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
21.1 Assembly point identified and known to everyone? |  | A |  |  |  |  | 0
21.2 Does the emergency plan developed? |  | A |  |  |  |  | 0
21.3 Fire Extinguishers are adequate in number and type, and inspected? |  | A |  |  |  |  | 0
21.4 Trauma center is provided with emergency first aid medicines? |  | A |  |  |  |  | 0
21.5 Accident and near miss reporting procedures are communicated with all project personnel? |  | A |  |  |  |  | 0
21.6 Are emergency contact number distributed on site and known to every single person? |  | A |  |  |  |  | 0
21.7 Carry out emergency drills periodically? |  | A |  |  |  |  | 0
21.8 Is the ambulance and fire truck provided to the project? |  | A |  |  |  |  | 0
21.9 Emergency access, egress, or fire exit are free of obstacles at all times and have been identified? |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 36
Rating |  |  |  | 0 | %
22.0 Environmental & welfare general items. | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
22.1 Is the environmental plan provided at the project? |  | A |  |  |  |  | 0
22.2 Waste management and segregation procedure are followed correctly? |  | A |  |  |  |  | 0
22.3 All waste types (domestic, sewage, hazardous, solid) are disposed by approved environmental services company? |  | A |  |  |  |  | 0
22.5 secondary containment is applied for chemical storage area and generators? |  | A |  |  |  |  | 0
22.6 Toilets must have periodic maintenance | [5 empty] | A | 4
22.7 Toilets are clean and detergents are provided? | [5 empty] | A | 4
22.8 Number of toilets are enough for workers and staff? | [5 empty] | A | 4
22.9 Sewage tank must be emptied periodically by a permitted contractor |  |  |  | A |  |  | 2
22.10 Sewage tank is designed underground and covered well? |  | A |  |  |  |  | 0
22.11 Is the drinking water provided at work place with enough quantity (4 liters for each person per day) | [5 empty] | A | 4
22.12 Is drinking water lab analysis carried out regularly? |  | A |  |  |  |  | 0
22.13 Noise measurement device is provided and noise monitored? |  | A |  |  |  |  | 0
22.14 Are the environmental signs been posted where it is necessary? |  | A |  |  |  |  | 0
22.15 Appropriate PPE for chemicals are provided? |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 18 | 56
Rating |  |  |  | 32.1429 | %
23.0 Management Support | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
23.1 Is there an adequate authorization given to HSE Department by project management? |  | A |  |  |  |  | 0
23.2 Is the PM or CM participating in the weekly HSE meeting and walk down? |  | A |  |  |  |  | 0
23.3 Have the PM, CM, Engineers, Supervisors are support implementing the company HSE manual & plan? |  | A |  |  |  |  | 0
23.4 Does the safety committee conduct the monthly meeting? |  | A |  |  |  |  | 0
23.5 Is the PM or CM Supporting HSE Disciplinary action taken by HSE Team? |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 0 | 20
Rating |  |  |  | 0 | %
General Site Performance total score |  |  |  | 372
General Site Performance total score including the N/A |  |  |  | 372
General Site Performance achieved Score |  |  |  | 52
General Site Performance percentage % |  |  |  | 13.9785 | %
SPMS Audit Total Rating Score
636
SPMS Audit Total Rating Score including the N/A
636
SPMS Audit Total Rating Score of this project
52
SPMS Audit Total Rating Score for this project percentage
8.1761 | %
Recommendations and corrective actions required:
1- arrangement of materials must be provided
2- safety management on site must be provided 3- safety & environment control measures must be provided on site. 4- PPE and fall protection must be provided on site.
The SPMS ratings are based on findings made by the auditor during the audit process. These ratings may go up or down depending on results of follow up audits.

## SHB Data
1- Health and Safety Organisation | 0
2- Project Health and Safety Plan | 0
3- General Health and Safety Communication | 0
4- Health and Safety Inductions | 0
5- Project Health and Safety Training | 0
6- Fire Safety Management | 0
7- Project Hazard & Risk Assessment | 0
8- Accident / Incident Management | 0
9- Subcontractors Risk Management / Communication | 0
10- Chemical management | 0
11- Health and Safety Audits | 0
12- Health and Safety Inspections | 0
13- General Site Performance | 15
14- Maintenance & Fabrication Workshop | 28.3333
15- Lifting and rigging operations | 11.1111
16- Hot works (cutting & Welding) | 0
17- Working at height and fall protection | 0
18- Camp accommodation | N/A
19- Electrical Hazards | 0
20- Excavations. | 29.1667
21- Emergency Preparedness. | 0
22- Environmental & welfare general items. | 32.1429
23- Management Support | 0

## TS Form
Atrium Quality Contractor |  |  |  |  | Code |  | HSE-PR02-F022
[5 empty] | Page no. |  | 1 OF 8
Health, Safety & Environmental Department |  |  |  |  | Rev. |  | 1
HSE site inspection performance evaluations |  |  |  |  | Date |  | April 22 2020
Project : Town Square | Inspection No: 4
Location: Town square - Cairo gate | Date of Inspection: 06/07/2025
Inspector: Tamer Agamy
SPMS Ratings for: (Town Square )
Positive Findings:
1- Warning and guidance sing are clear and well distributed
2/ access and roads clear and free Frome obstacle
3/good safety documents
Negative findings and Areas for Improvement:
1- Poor arrangement of materials
2- some of subcontractors not committed wearing PPE especially safety shoes
Date of Next Inspection:
Name of Inspector: Tamer Agamy |  | Date: 06/07/2025
SPMS Element | Score
Health and Safety Management
1.0 HSE Organisation | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
1.1 HSE Policy Issued and Displayed | [5 empty] | A | 4
1.2 Management HSE Responsibilities and Duties in place | [5 empty] | A | 4
1.3 Responsibilities and Duties understood & followed |  |  |  |  | A |  | 3
1.4 HSE Appointments made for Fire, First Aid, etc. | [5 empty] | A | 4
1.5 Adequate HSE Staff appointed for the contract | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 19 | 20
Percentage |  |  |  | 95 | %
2.0 Project Health and Safety Plan | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
2.1 HSE Plan in Place and Implemented | [5 empty] | A | 4
2.2 Plan up to Date with project requirements and risk | [5 empty] | A | 4
2.3 Management Reviews completed and Plan Updated | [5 empty] | A | 4
2.4 Issued to Senior Management | [5 empty] | A | 4
2.5 Issued to Contractors |  |  |  |  | A |  | 3
|  | Total Score |  |  |  |  | 19 | 20
Rating |  |  |  | 95 | %
3.0 General HSE Communication | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
3.1 Toolbox talks completed as per schedule / Requirements | [5 empty] | A | 4
3.2 Specific Toolbox talks to Project / Requirements | [5 empty] | A | 4
3.3 Toolbox talks relevant to weekly taskes |  |  |  |  | A |  | 3
3.4 Daily brief to HSE issues on site |  |  |  |  | A |  | 3
3.5 HSE Notice Boards Posted / Up to Date |  |  |  |  | A |  | 3
3.6 Key information communicated to Engineer / Supervisores |  |  |  |  | A |  | 3
3.7 Project management committed to guarantee that the contractors provide an appropriate PPEs for the assigned job. | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 24 | 28
Rating |  |  |  | 85.7143 | %
SPMS Element | Score
Inspection
4.0 Health and Safety Inductions | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
4.1 HSE Induction Specific to Project/ PM/ CM | [5 empty] | A | 4
4.2 Project management committed to refer the employees / contractor to the OH&S Department before starting work to obtain HSE induction and ensure its compliance with safety standards on first Day of Work. | [5 empty] | A | 4
4.3 Subcontractors employees included & sign | [5 empty] | A | 4
4.4 Induction Records and Registers Maintained. | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 16 | 16
Rating |  |  |  | 100 | %
5.0 Project HSE Training | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
5.1 HSE Training Needs Identified |  |  |  | A |  |  | 2
5.2 In line with project requirements and risk areas | [5 empty] | A | 4
5.3 Reviews / follow-up of training completed | [5 empty] | A | 4
5.4 Task /Trade Training Conducted work permit related | [5 empty] | A | 4
5.5 Records /Registers Maintained | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 18 | 20
Rating |  |  |  | 90 | %
6.0 Fire Safety Management | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
6.1 Fire risk assessments completed for all areas |  |  |  |  | A |  | 3
6.2 Personnel trained in fire safety arrangements | [5 empty] | A | 4
6.3 Fire Control zones identified and protected | [5 empty] | A | 4
6.4 Fire Incidents investigated and actions closed out | N/A
6.5 Permit to work system for high risk activities / fire exposure | [5 empty] | A | 4
6.6 Fire Management Procedure in Place |  |  |  |  | A |  | 3
6.7 Fire Fighting Equipment Checked / Log of Inspections | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 22 | 24
Rating |  |  |  | 91.6667 | %
HSE Management total score |  |  |  | 144
HSE Management total score including the N/A |  |  |  | 128
HSE Management achieved score |  |  |  | 118
HSE Management percentage % |  |  |  | 92.1875 | %
SPMS Element | Score
Risk Management
7.0 Project Hazard & Risk Assessment | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
7.1 General Hazard and Risk Assessment completed ( project) | [5 empty] | A | 4
7.2 Reviewed and Updated inline with project activities | [5 empty] | A | 4
7.3 workforce attaned the risk Decision | [5 empty] | A | 4
7.4 Control Measures identified and implemented |  |  |  |  | A |  | 3
7.5 Personnel Trained/Competent to conduct risk assessments |  |  |  |  | A |  | 3
|  | Total Score |  |  |  |  | 18 | 20
Rating |  |  |  | 90 | %
8.0 Accident / Incident Management | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
8.1 Procedure developed for the project and implemented | [5 empty] | A | 4
8.2 Investigation completed with right root cause | [5 empty] | A | 4
8.3 Investigation Reports issued to senior management | [5 empty] | A | 4
8.4 Root cause reviewed with the procedures | [5 empty] | A | 4
8.5 Projects Management Involved in Investigation Process | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 20 | 20
Rating |  |  |  | 100 | %
9.0 Subcontractors Risk Management / Communication | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
9.1 Generic Hazard and Risk Identified for Work Activities | [5 empty] | A | 4
9.2 Incorporated into overall risk profile for the project | [5 empty] | A | 4
9.3 HSE Alerts Issued | [5 empty] | A | 4
9.4 Contractors inducted and informed of key processes | [5 empty] | A | 4
9.5 Method Statements produced by subcontractors | [5 empty] | A | 4
9.6 A pre-start meeting must be held with all sub-contractors |  |  |  |  | A |  | 3
9.7 Committed to apply A full scope evaluation for the sub-contractors to ensure that they are complying to HSE rules (Induction, PPE, underage policy, pre-start meeting, etc. |  |  |  | A |  |  | 2
|  | Total Score |  |  |  |  | 25 | 28
Rating |  |  |  | 89.2857 | %
10.0 Chemical management | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
10.1 Storage conditions are acceptable in storage areas |  |  |  |  | A |  | 3
10.2 All chemicals are clearly identified | [5 empty] | A | 4
10.3 Chemical products used on site are in second containment |  | A |  |  |  |  | 0
10.4 Spill kits are available on site at the areas where there potentially a spill could happen | N/A
10.5 MSDS are available for the chemical use | [5 empty] | A | 4
10.6 Warehouse committed not to receiving any supply of chemicals without supplying MSDS to the HSE Department In the project. | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 15 | 20
Rating |  |  |  | 75 | %
Risk Management total score |  |  |  | 80
Risk Management total score including the N/A |  |  |  | 88
Risk Management achieved score |  |  |  | 78
Risk Management percentage % |  |  |  | 88.6364 | %
n
n
SPMS Element | Score
Inspections
11.0 HSE inspection | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
11.1 HSE Inspection planned and conducted to programme | [5 empty] | A | 4
11.2 An inspection must be done by a competent person | [5 empty] | A
11.3 Results of Inspection communicated and action identified | [5 empty] | A | 4
11.4 Inspection covering health and safety plan + key risk of project | [5 empty] | A | 4
11.5 Inspection Analysis in line with works and risk rated | [5 empty] | A | 4
11.6 Results discussed in senior management meetings | [5 empty] | A | 4
11.7 The Supervisors & Sub-contractors Committed to use an inspected equipments. | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 24 | 24
Rating |  |  |  | 100 | %
12.0 Cold Work Perimt | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
12.1 Are the work permit in Place | [5 empty] | A | 4
12.2 Work Permit including all work related | [5 empty] | A | 4
12.3 Work Permit signed from each responsibles | [5 empty] | A | 4
12.4 Work permit closed on time |  |  |  |  | A |  | 3
12.5 The risks and preventive measures related to the work permit are identified by the responsible supervisor and followed up and implemented |  |  |  |  | A |  | 3
12.6 Work Permit log avalibale on HSE Office | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 22 | 24
Rating |  |  |  | 91.6667 | %
Inspections total score |  |  |  | 40
Inspections total score including the N/A |  |  |  | 48
Inspections achieved score |  |  |  | 46
Inspections percentage % |  |  |  | 95.8333 | %
SPMS Element | Score
General Site Performance
13.0 General Site Performance | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
13.1 Workers using correct PPE | [5 empty] | A | 4
13.2 Tools and equipment being used by operative safe to use |  |  |  |  | A |  | 3
13.3 Safety Sign visible and located in prominent areas |  |  |  |  | A |  | 3
13.4 Permit in place for work activity and in compliance |  |  |  |  | A |  | 3
13.5 Emergency access is clear to be in use |  |  |  |  | A |  | 3
13.6 Electrical leads/equipment in safe condition & protected |  |  |  |  | A |  | 3
13.7 Housekeeping maintained to acceptable levels of safety |  |  |  |  | A |  | 3
13.8 Fire Protection measures in place .i.e. fire points | [5 empty] | A | 4
13.9 Committed to apply up An appropriate lighting system during night shift | [5 empty] | A | 4
13.10 Walkways and common areas free from obstructions | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 34 | 40
Rating |  |  |  | 85 | %
14.0 Maintenance & Fabrication Workshop | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
14.1 Lighting is sufficient |  |  |  |  | A |  | 3
14.2 Grinding machine has a protection cover and adequate desk. | [5 empty] | A | 4
14.3 Electrical equipment and tools are inspected with color codes. | [5 empty] | A | 4
14.4 Flammable materials are secured and stored |  |  |  |  | A |  | 3
14.5 Firefighting system planed and implemented | [5 empty] | A | 4
14.6 Hand tools are in good condition and quality. | [5 empty] | A | 4
14.7 Handling used oil procedures are followed in a safe practice an |  |  |  |  | A |  | 3
14.8 All precautions for hot work (welding, cutting) are implemented. | [5 empty] | A | 4
14.9 Housekeeping and material arrangement . |  |  |  |  | A |  | 3
14.10 Are all employees have a suitable PPE and appropriate to their activates? | [5 empty] | A | 4
Smoking prohibition signs are posted in the place and clear for all workers and visitors. |  |  |  |  | A |  | 3
14.12 Mobile tank must have an earthing | N/A
14. 13 Safety signs are available in all workplace. |  |  |  |  | A |  | 3
14.14 Floors are flatting and clean against slipping hazards. | N/A
14.15 Committed to provide Skill level certificate for (grinding machine operator). | N/A
14.16 Waste management procedures are followed. |  |  |  |  | A |  | 3
|  | Total Score |  |  |  |  | 45 | 52
Rating |  |  |  | 86.5385 | %
15.0 Lifting and rigging operations | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
15.1 Does all lifting and rigging equipment are inspected and color coded. | [5 empty] | A | 4
15.2 Calibration certificates for all lifting equipment and gears are valid and provided inside the crane. | [5 empty] | A | 4
15.3 Are the operators, riggers and banks man trained and competent? | [5 empty] | A | 4
15.4 Pre use inspection is carried out? | [5 empty] | A | 4
15.5 Is the critical lifting operation assessed and planned by competent person? | [5 empty] | A | 4
15.6 A drug test must be held for crane operators & riggers | [5 empty] | A | 4
15.7 A communiction method between operators & riggers must be provided, tested and sufficient. |  |  |  |  | A |  | 3
15.8 Skill level certificate must be provided for (operators, riggers) |  |  |  |  | A |  | 2
15.9 Operators licenses are available and valid | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 33 | 36
Rating |  |  |  | 91.6667 | %
16.0 Hot works (cutting & Welding) | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
16.1 Hot work permit copy is provided at work place. |  |  |  |  | A |  | 3
16.2 Are the work permit signed from each one | [5 empty] | A | 4
16.3 Are the work Permit is closed on time | [5 empty] | A | 4
16.4 Fire extinguishers and blankets are available on site for the hot works. | [5 empty] | A | 4
16.5 Are all welding machines inspected and in a good condition and color coded. | [5 empty] | A | 4
16.6 Grinding machine has a protection cover and adequate desk. | N/A
|  | Total Score |  |  |  |  | 19 | 20
Rating |  |  |  | 95 | %
17.0 Working at height and fall protection | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
17.1 Personal fall arrest system are correctly used (well worn, use of suitable anchor point…) | [5 empty] | A | 4
17.2 All scaffolds are in good conditions and inspected and tagged. By the right scaffolding inspectors |  |  |  |  | A |  | 3
17.3 Safety Harnesses and lanyard in a good condition and used correctly. | [5 empty] | A | 4
17.4 Are the scaffolders trained and competent?( Training Sheet avalibale) | [5 empty] | A | 4
17.5 Does all workers assigned to work at heights received training? ( Training Sheet avalibale) | [5 empty] | A | 4
17.6 Does the scaffold design prevent falling of people and objects (toe board, handrails, midrails and access ladder) | [5 empty] | A | 4
17.7 Are the scaffold material in a good condition and quality? | [5 empty] | A | 4
17.8 If the scaffold highest more than 7 meters is attached in fixed wall or anchor point 4 meters. | N/A
17.9 Committed to provide Skill level certificate for (scaffold technicians) | [5 empty] | A | 4
17.10 Stop any ongoing work during the erictionof scaffold or if there are works at heights in this area |  |  |  |  | A |  | 3
17.11 A design or a calculation sheet must be provided for scaffold |  |  |  |  | A |  | 3
17.12 are the scaffolding logs are avalibale |  |  |  |  | A |  | 3
|  | Total Score |  |  |  |  | 40 | 44
Rating |  |  |  | 90.9091 | %
18.0 Camp accommodation | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
18.1 Level of housekeeping and cleanliness of the rooms is acceptable? | N/A
18.2 Emergency evacuation procedures are in place and followed | N/A
18.3 Assembly point identified and known to everyone? | N/A
18.4 Toilets are clean and soap is provided? | N/A
18.5 Number of toilets are enough for worker? | N/A
18.6 Sewage tank is designed underground and covered well? | N/A
18.7 Sewage disposal is carrying out by approved company? | N/A
18.8 Gas cylinders are used in cooking are secured and placed in a safe zone and equipped with regulator. | N/A
18.9 Firefighting system planed and implemented, adequate number of fire extinguishers are in place and inspected. | N/A
|  | Total Score |  |  |  |  | 0 | 0
Rating |  |  |  | N/A | %
19.0 Electrical Hazards | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
19.1 All electrical installations/materials including temporary wiring, panels, boxes and fittings are grounded? | [5 empty] | A | 4
19.2 All electrical panels and fittings are closed, locked, are provided with external emergency breakers and correctly identified with electrical risk tags | [5 empty] | A | 4
19.3 All electrical panels & generators must be top guarded to be protected from rain & sun | [5 empty] | A | 4
19.4 All electrical panels must contain a GFCI & a mirror |  |  |  | A |  |  | 2
19.5 An extinguisher is present near each electrical panel, generator |  |  |  |  | A |  | 3
19.6 All electrical materials (cables, tools…) are in good condition, quarterly inspected and marked? | [5 empty] | A | 4
19.7 Safe cables management is applied at the work place? | [5 empty] | A | 4
19.8 Lockout & tag out (LOTO) system is implemented and followed by all people? |  | A |  |  |  |  | 0
|  | Total Score |  |  |  |  | 25 | 32
Rating |  |  |  | 78.125 | %
20.0 Excavations. | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
20.1 Are all underground hazard and utilities (pipe lines, elec. cables, communication….etc.) been identified? |  |  |  |  | A |  | 3
20.2 Excavation methods (shoring, pinching and sloping) are used to prevent collapse of excavation? | [5 empty] | A | 4
20.3 Warning signs and hard barriers around excavation are in good state to prevent falling people and equipment? |  |  |  |  | A |  | 3
20.4 Daily excavation inspection sheet is correctly fulfilled for each excavation? |  |  |  |  | A |  | 3
20.5 Suitable and safe means of access/egress (1 access ramp or ladder every 10 meters) |  |  |  |  | A |  | 3
20.6 Excavation permit copy in place? | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 20 | 24
Rating |  |  |  | 83.3333 | %
21.0 Emergency Preparedness. | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
21.1 Assembly point identified and known to everyone? | [5 empty] | A | 4
21.2 Does the emergency plan developed? | [5 empty] | A | 4
21.3 Fire Extinguishers are adequate in number and type, and inspected? | [5 empty] | A | 4
21.4 Trauma center is provided with emergency first aid medicines? | N/A
21.5 Accident and near miss reporting procedures are communicated with all project personnel? | [5 empty] | A | 4
21.6 Are emergency contact number distributed on site and known to every single person? | [5 empty] | A | 4
21.7 Carry out emergency drills periodically? | [5 empty] | A | 4
21.8 Is the ambulance and fire truck provided to the project? | [5 empty] | A | 4
21.9 Emergency access, egress, or fire exit are free of obstacles at all times and have been identified? | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 32 | 32
Rating |  |  |  | 100 | %
22.0 Environmental & welfare general items. | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
22.1 Is the environmental plan provided at the project? | [5 empty] | A | 4
22.2 Waste management and segregation procedure are followed correctly? | [5 empty] | A | 4
22.3 All waste types (domestic, sewage, hazardous, solid) are disposed by approved environmental services company? | [5 empty] | A | 4
22.5 secondary containment is applied for chemical storage area and generators? |  | A |  |  |  |  | 0
22.6 Toilets must have periodic maintenance | [5 empty] | A | 4
22.7 Toilets are clean and detergents are provided? | [5 empty] | A | 4
22.8 Number of toilets are enough for workers and staff? |  |  |  |  | A |  | 3
22.9 Sewage tank must be emptied periodically by a permitted contractor | [5 empty] | A | 4
22.10 Sewage tank is designed underground and covered well? | [5 empty] | A | 4
22.11 Is the drinking water provided at work place with enough quantity (4 liters for each person per day) | [5 empty] | A | 4
22.12 Is drinking water lab analysis carried out regularly? | [5 empty] | A | 4
22.13 Noise measurement device is provided and noise monitored? | [5 empty] | A | 4
22.14 Are the environmental signs been posted where it is necessary? | [5 empty] | A | 4
22.15 Appropriate PPE for chemicals are provided? |  |  |  |  | A |  | 3
|  | Total Score |  |  |  |  | 50 | 56
Rating |  |  |  | 89.2857 | %
23.0 Management Support | N/A | 0 | 1 | 2 | 3 | 4 | Achieved score | Total Score
23.1 Is there an adequate authorization given to HSE Department by project management? | [5 empty] | A | 4
23.2 Is the PM or CM participating in the weekly HSE meeting and walk down? | [5 empty] | A | 4
23.3 Have the PM, CM, Engineers, Supervisors are support implementing the company HSE manual & plan? |  |  |  |  | A |  | 3
23.4 Does the safety committee conduct the monthly meeting? | N/A
23.5 Is the PM or CM Supporting HSE Disciplinary action taken by HSE Team? | [5 empty] | A | 4
|  | Total Score |  |  |  |  | 15 | 16
Rating |  |  |  | 93.75 | %
General Site Performance total score |  |  |  | 372
General Site Performance total score including the N/A |  |  |  | 352
General Site Performance achieved Score |  |  |  | 313
General Site Performance percentage % |  |  |  | 88.9205 | %
SPMS Audit Total Rating Score
636
SPMS Audit Total Rating Score including the N/A
616
SPMS Audit Total Rating Score of this project
555
SPMS Audit Total Rating Score for this project percentage
90.0974 | %
Recommendations and corrective actions required:
All project workers must be required to wear personal protective equipment.
This document is a property of " Atrium Quality Contractors " and not to be copied or printed for use outside “Atrium Quality Contractors " without permission from the issuer, "HSE Department", or else it would be an attack on intellectual property rights of the company and be subject to legal accountability.
The SPMS ratings are based on findings made by the auditor during the audit process. These ratings may go up or down depending on results of follow up audits.

## TS Data
1- Health and Safety Organisation | 95
2- Project Health and Safety Plan | 95
3- General Health and Safety Communication | 85.7143
4- Health and Safety Inductions | 100
5- Project Health and Safety Training | 90
6- Fire Safety Management | 91.6667
7- Project Hazard & Risk Assessment | 90
8- Accident / Incident Management | 100
9- Subcontractors Risk Management / Communication | 89.2857
10- Chemical management | 75
11- Health and Safety Audits | 100
12- Health and Safety Inspections | 91.6667
13- General Site Performance | 85
14- Maintenance & Fabrication Workshop | 86.5385
15- Lifting and rigging operations | 91.6667
16- Hot works (cutting & Welding) | 95
17- Working at height and fall protection | 90.9091
18- Camp accommodation | N/A
19- Electrical Hazards | 78.125
20- Excavations. | 83.3333
21- Emergency Preparedness. | 100
22- Environmental & welfare general items. | 89.2857
23- Management Support | 93.75

## Final Data
Standards | SHB | TS | SHB Performance | TS Performance | Difference | Include in analysis
1- Health and Safety Organisation | 0 | 95 | low | high | 95 | Yes
2- Project Health and Safety Plan | 0 | 95 | low | high | 95 | Yes
3- General Health and Safety Communication | 0 | 85.71 | low | high | 85.71 | Yes
4- Health and Safety Inductions | 0 | 100 | low | high | 100 | Yes
5- Project Health and Safety Training | 0 | 90 | low | high | 90 | Yes
6- Fire Safety Management | 0 | 91.67 | low | high | 91.67 | Yes
7- Project Hazard & Risk Assessment | 0 | 90 | low | high | 90 | Yes
8- Accident / Incident Management | 0 | 100 | low | high | 100 | Yes
9- Subcontractors Risk Management / Communication | 0 | 89.29 | low | high | 89.29 | Yes
10- Chemical management | 0 | 75 | low | high | 75 | Yes
11- Health and Safety Audits | 0 | 100 | low | high | 100 | Yes
12- Health and Safety Inspections | 0 | 91.67 | low | high | 91.67 | Yes
13- General Site Performance | 15 | 85 | low | high | 70 | Yes
14- Maintenance & Fabrication Workshop | 28.33 | 86.54 | low | high | 58.21 | Yes
15- Lifting and rigging operations | 11.11 | 91.67 | low | high | 80.56 | Yes
16- Hot works (cutting & Welding) | 0 | 95 | low | high | 95 | Yes
17- Working at height and fall protection | 0 | 90.91 | low | high | 90.91 | Yes
18- Camp accommodation | [5 empty] | No
19- Electrical Hazards | 0 | 78.13 | low | high | 78.13 | Yes
20- Excavations. | 29.17 | 83.33 | low | high | 54.16 | Yes
21- Emergency Preparedness. | 0 | 100 | low | high | 100 | Yes
22- Environmental & welfare general items. | 32.14 | 89.29 | low | high | 57.15 | Yes
23- Management Support | 0 | 93.75 | low | high | 93.75 | Yes
TOTAL | 8.18 | 90.1 | low | high | 81.92 | No

## Dashboard
Internal inspection Analysis
POWER OF TS
POWER OF SHB

## Dashboard (2)
Internal inspection Analysis

## pivot
Row Labels | Average of SHB | Average of TS | Include in analysis | Yes | Row Labels | Power of TS | Power of SHB
1- Health and Safety Organisation | 0 | 95 |  |  | TOTAL | 90.1 | 8.18
10- Chemical management | 0 | 75 | Row Labels | Count of Standards | Grand Total | 90.1 | 8.18
11- Health and Safety Audits | 0 | 100 | low | 22
12- Health and Safety Inspections | 0 | 91.67 | Grand Total | 22 | Row Labels | Sum of SHB
13- General Site Performance | 15 | 85 |  |  | 14- Maintenance & Fabrication Workshop | 28.33
14- Maintenance & Fabrication Workshop | 28.33 | 86.54 | Include in analysis | Yes | 20- Excavations. | 29.17
15- Lifting and rigging operations | 11.11 | 91.67 |  |  | 22- Environmental & welfare general items. | 32.14
16- Hot works (cutting & Welding) | 0 | 95 | Row Labels | Count of Standards | Grand Total | 89.64
17- Working at height and fall protection | 0 | 90.91 | high | 22
18- Camp accommodation |  |  | Grand Total | 22
19- Electrical Hazards | 0 | 78.13
2- Project Health and Safety Plan | 0 | 95 |  |  | Row Labels | Sum of TS
20- Excavations. | 29.17 | 83.33 |  |  | 11- Health and Safety Audits | 100
21- Emergency Preparedness. | 0 | 100 | Row Labels | TS over SHB | 21- Emergency Preparedness. | 100
22- Environmental & welfare general items. | 32.14 | 89.29 | 1- Health and Safety Organisation | 95 | 4- Health and Safety Inductions | 100
23- Management Support | 0 | 93.75 | 10- Chemical management | 75 | 8- Accident / Incident Management | 100
3- General Health and Safety Communication | 0 | 85.71 | 11- Health and Safety Audits | 100 | Grand Total | 400
4- Health and Safety Inductions | 0 | 100 | 12- Health and Safety Inspections | 91.67
5- Project Health and Safety Training | 0 | 90 | 13- General Site Performance | 70
6- Fire Safety Management | 0 | 91.67 | 14- Maintenance & Fabrication Workshop | 58.21
7- Project Hazard & Risk Assessment | 0 | 90 | 15- Lifting and rigging operations | 80.56
8- Accident / Incident Management | 0 | 100 | 16- Hot works (cutting & Welding) | 95
9- Subcontractors Risk Management / Communication | 0 | 89.29 | 17- Working at height and fall protection | 90.91
Grand Total | 5.2614 | 90.7709 | 19- Electrical Hazards | 78.13
|  |  | 2- Project Health and Safety Plan | 95
|  |  | 20- Excavations. | 54.16
|  |  | 21- Emergency Preparedness. | 100
|  |  | 22- Environmental & welfare general items. | 57.15
|  |  | 23- Management Support | 93.75
|  |  | 3- General Health and Safety Communication | 85.71
|  |  | 4- Health and Safety Inductions | 100
|  |  | 5- Project Health and Safety Training | 90
|  |  | 6- Fire Safety Management | 91.67
|  |  | 7- Project Hazard & Risk Assessment | 90
|  |  | 8- Accident / Incident Management | 100
|  |  | 9- Subcontractors Risk Management / Communication | 89.29
|  |  | Grand Total | 1881.21